## Sheet1
Sprint Backlog sample template for Social media application (Detailed Estimate for current sprint)
ID |  | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Sprint 1 | User Authentication | Authentication | As a user, I want to securely access the app. | Must | In Progress | 1. The user can register with a valid email and password. 2. User receives a confirmation email for account activation. 3. User can log in with registered credentials. 4. Password reset functionality is secure and straightforward. | Secure password hashing and storage. Account lockout after multiple failed login attempts. | Response time for authentication actions should be less than 2 seconds. Password reset emails should be delivered within 5 minutes. | 5 days | 4 days
4 |  | Multi-language Support | Localization | As a global user, I want to use the app in my preferred language. | Must | Ready for Dev | 1. User can select preferred language in settings. 2. All app content is displayed in the selected language 3. Translations are accurate and culturally sensitive. | Implement language selection in user settings. Use localization for all UI text and content. | Translation process should be documented and repeatable.- Support at least 5 major languages. | 5 days | 5 Days
5 |  | Performance Enhancement | Performance | As a user, I want a fast and responsive app. | Must | In Testing | 1. App loads within 3 seconds on average. 2. Smooth navigation between screens without delays. 3. Load testing confirms stability under peak usage. | Optimize database queries and indexing. Implement caching for frequently accessed data. | Response time for critical user actions should be less than 2 seconds.- Monitor and optimize server resource usage. | 7 days
9 |  | Bug Fixes | Bug Fixes | As a user, I want a bug-free experience. | Must | In Progress | 1. Resolved login error for users with special characters in passwords 2. Fixed image loading issue in the gallery. 3. Regression testing confirms bug resolution. | Identify and fix specific bugs reported by users and testing. Implement automated tests to prevent regression. | Critical bugs should be resolved within 48 hours of discovery. Implement a bug-tracking system for efficient reporting and resolution. | 7 days
[7 empty] | Assignee : |  | Due date :